## README
Caboodle — Jira Backlog Organized by Module
Purpose | 225 open tickets (Backlog / In Progress / In Staging / Ready for Production / Reopened) classified into the Caboodle module hierarchy to plan the 3-month sprint ahead of new-client onboarding.
How it was built | Each ticket was assigned an Area + Caboodle Module by reading its Summary (which references the module), with the original Jira "Module" column used as backup. The [FE]/[BE] tag was parsed from the summary into the FE/BE column for engineer allocation.
TABS
Module Summary | Live count of tickets per module, broken out by status, priority, and FE vs BE. Formula-driven — edits to the Master tab flow through automatically.
All Tickets (Master) | Every ticket with its assigned Area, Module and FE/BE tag. This is the source of truth; the area tabs and summary read from it.
Broker Dashboard / Brand / Reports / Admin / Platform | One tab per Area, tickets grouped under their module heading and sorted by priority.
NOTES & JUDGMENT CALLS
Category Review | Appears in two places: under Broker Dashboard (the broker-side review tool) and under Reports as "Category Review Report". Tickets tagged "Reports ¦ Category Review" went to the report; the rest to Broker Dashboard.
Trade Spend | "Trade Spend Sandbox / TSS / EDLP / Everyday Allowance" → Brand module Trade Spend Sandbox. "Trade Spend Roll Up / Rollup Report" → Reports module Trade Spend Rollup.
Platform & Cross-Cutting | 30 tickets that do not belong to any single module — DB indexing, code refactor, caching, email service, QA/UX audits, big-data upload wizard, Ask Caboodle (AI), Tableau, margin calculator. Worth scoping separately from module work.
Two new reports | "Banner-to-DC Reporting" is flagged as a new report (not in the current 8-report list).
Re-binning | Because the Area & Module columns live on every row, you can re-sort or re-classify any ticket and the Module Summary updates instantly.

## Module Summary
Tickets by Caboodle Module
Area | Caboodle Module | Total | Backlog | In Progress | In Staging | Ready for Prod | Reopened | Highest | High | Medium | Low | FE | BE
Broker Dashboard | Market Overview | 6 | 5 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 1
Broker Dashboard | Promotional Management | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0 | 2
Broker Dashboard | Category Review | 11 | 9 | 1 | 0 | 0 | 1 | 1 | 10 | 0 | 0 | 0 | 0
Broker Dashboard | Distributor APL | 4 | 4 | 0 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 0
Broker Dashboard | Files | 3 | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0
Broker Dashboard | Broker Dashboard (General) | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 0 | 1
Brand | Product Specs | 8 | 5 | 1 | 0 | 0 | 2 | 1 | 4 | 2 | 1 | 0 | 2
Brand | Distributors | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Brand | Retailers | 3 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 2
Brand | Contacts | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Brand | Pipeline | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0 | 0
Brand | Trade Spend Sandbox | 37 | 28 | 1 | 3 | 4 | 1 | 5 | 21 | 5 | 6 | 2 | 1
Brand | Promotional Calendar | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
Reports | Broker Market Activities | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Reports | Category Review Report | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0
Reports | Retail Reports | 4 | 3 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 1 | 0
Reports | Sales Tracker | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Reports | Trade Spend Rollup | 5 | 3 | 1 | 0 | 0 | 1 | 3 | 2 | 0 | 0 | 0 | 2
Reports | Monthly Report | 7 | 5 | 1 | 0 | 1 | 0 | 2 | 3 | 0 | 2 | 0 | 1
Reports | SPINS | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0
Reports | Distributor Report | 16 | 11 | 3 | 2 | 0 | 0 | 3 | 11 | 1 | 1 | 1 | 0
Reports | Banner-to-DC (New Report) | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Reports | Reports (Unspecified) | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
Admin | CRM Data Upload | 11 | 10 | 0 | 0 | 0 | 1 | 1 | 5 | 1 | 4 | 0 | 1
Admin | Data Mapping | 19 | 13 | 3 | 0 | 2 | 1 | 5 | 8 | 1 | 5 | 2 | 5
Admin | User Management | 17 | 16 | 1 | 0 | 0 | 0 | 0 | 2 | 6 | 9 | 0 | 1
Admin | Admin (General) | 20 | 19 | 1 | 0 | 0 | 0 | 0 | 3 | 4 | 13 | 2 | 5
Platform & Cross-Cutting | Infrastructure / Cross-Cutting | 28 | 22 | 4 | 0 | 1 | 1 | 2 | 14 | 6 | 6 | 1 | 4
| GRAND TOTAL | 225 | 181 | 21 | 6 | 8 | 9 | 30 | 111 | 33 | 51 | 9 | 29

## All Tickets (Master)
Issue Key | Type | Summary | Area | Caboodle Module | FE/BE | Priority | Status | Assignee | Reporter | Created | Updated | Due / Note
CS-146 | Task | [BE] Module on off | Admin | Admin (General) | BE | Medium | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/3/2023 | 12/3/2023 | Discuss
CS-147 | Task | [FE] Module on off | Admin | Admin (General) | FE | Medium | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 12/3/2023 | 4/27/2025 | Discuss
CS-190 | Task | Caboodle Phase 2 Requirements | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Medium | Backlog |  | Md Mashiul Azam Chowdhury | 12/9/2023 | 2/5/2024
CS-234 | Task | [BE] Promotional Management - Push date submission to brand side | Broker Dashboard | Promotional Management | BE | Medium | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/21/2023 | 12/21/2023 | Discuss
CS-232 | Task | [BE] Promotional Management - Published distributor pricing for Promo Submissions | Broker Dashboard | Promotional Management | BE | Low | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/21/2023 | 12/21/2023 | Discuss
CS-245 | Task | [BE] Admin - Activity Log | Admin | Admin (General) | BE | Low | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/21/2023 | 12/21/2023 | Discuss
CS-246 | Task | [FE] Admin - Activity Log | Admin | Admin (General) | FE | Low | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 12/21/2023 | 4/27/2025 | Discuss
CS-247 | Task | [BE] Admin - Upload Effeciency | Admin | Admin (General) | BE | Low | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/21/2023 | 12/21/2023 | Discuss
CS-280 | Task | [BE] Product Specs Add a text box for Shelf Life and another for Attributes. Doesn't need to be in the file upload | Brand | Product Specs | BE | Medium | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 1/1/2024 | 1/1/2024 | Don't Do
CS-376 | Task | Product Specs - Add Chck Box for Manufacturer Discontinued | Brand | Product Specs | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 2/10/2024 | 4/27/2025 | Complete?
CS-405 | Task | Monitoring Service | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Medium | Backlog | Bijoy Chandra Nath | Bijoy Chandra Nath | 2/29/2024 | 9/25/2025 | ??
CS-478 | Bug | Product Specs Price List ¦ Price Change is not flowing thru Trade Spend for promos after date change | Brand | Product Specs | Unspec | Highest | Reopened | Bijoy Chandra Nath | Constance Wolfe | 4/25/2024 | 7/9/2024
CS-487 | Task | [BE] Saving Banner SKU Failed Records and automatically adding them back into the system once we've matched up the unrecognized banners from the Data Mapping section | Admin | Data Mapping | BE | Medium | Backlog | Bijoy Chandra Nath | Bijoy Chandra Nath | 4/29/2024 | 9/25/2025 | ??
CS-496 | Bug | Banner Upload Error Messaging | Admin | CRM Data Upload | Unspec | High | Backlog |  | Constance Wolfe | 5/2/2024 | 11/10/2025 | ??
CS-514 | Task | Optimize the tables to ensure that the site remains unaffected even with a large amount of data. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 5/7/2024 | 5/7/2024 | Complete?
CS-517 | Task | Apply Indexing Mechanism in Database | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 5/7/2024 | 9/25/2025 | Provide update
CS-512 | Task | Check if we can further utilize caching from any other areas | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 5/7/2024 | 5/7/2024 | ??
CS-518 | Task | Automatically Remove Deleted Records After Certain Period Of Time | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Medium | Backlog | Bijoy Chandra Nath | Bijoy Chandra Nath | 5/7/2024 | 9/25/2025 | ??
CS-519 | Task | [BE] Re-Structuring The Code Base | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | BE | Medium | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 5/7/2024 | 9/25/2025 | Provide update
CS-532 | Task | Trade Spend ¦ Promo Event Details ¦ Is it possible to add a sku without going thru the stepper again? | Brand | Trade Spend Sandbox | Unspec | Low | Backlog |  | Constance Wolfe | 5/28/2024 | 5/28/2024 | Complete?
CS-562 | Task | [BE] Implement User-Based Permission Control Module | Admin | User Management | BE | Medium | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 6/24/2024 | 9/25/2025 | Provide update
CS-570 | Task | Filters Updates | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Highest | Reopened | Md Mashiul Azam Chowdhury | Heather Whittier | 7/9/2024 | 4/27/2025
CS-617 | Sub-task | [BE] Manufacture Discontinue ¦ MFR Disco Status | Brand | Product Specs | BE | High | In Progress | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 9/26/2024 | 1/7/2025 | Provide update
CS-653 | Task | Caboodle Broker ¦ Trade Spend Sandbox should report to Promotional Management (not Promo Planning) | Brand | Trade Spend Sandbox | Unspec | High | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 11/26/2024 | 11/6/2025 | Provide update
CS-658 | Bug | Files ¦ Files Tree Display issues See image of overlapping folders | Broker Dashboard | Files | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 12/6/2024 | 4/27/2025 | ??
CS-675 | Sub-task | Empowering Brand owner's edit in Banner SKU section | Admin | Admin (General) | Unspec | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/26/2024 | 9/25/2025 | ??
CS-688 | Task | [BE] Implement read tables for Market Overview | Broker Dashboard | Market Overview | BE | High | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 2/5/2025 | 9/25/2025 | Provide update
CS-701 | Story | Share link of pages like in google and restrict it to view only | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Low | Backlog | Constance Wolfe | Md Mashiul Azam Chowdhury | 2/17/2025 | 11/6/2025 | ??
CS-725 | Story | Trade Spend Promotion Module | Brand | Trade Spend Sandbox | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Bijoy Chandra Nath | 3/12/2025 | 3/12/2025 | ??
CS-894 | Epic | Issues from QA audit | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | QA | Low | Backlog |  | Fariha Jabin | 5/5/2025 | 11/6/2025 | ??
CS-955 | Epic | UX Audit | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Abdullah Al Mahmud | Md Mashiul Azam Chowdhury | 5/15/2025 | 11/6/2025 | ??
CS-973 | Story | Regression Test | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | QA | Low | Backlog |  | Fariha Jabin | 5/26/2025 | 5/29/2025 | ??
CS-992 | Sub-task | [BE] Retailer details page - Category search returning irrelevant results | Brand | Retailers | BE | Low | In Progress | Bijoy Chandra Nath | Fariha Jabin | 6/4/2025 | 9/25/2025 | Provide update
CS-1022 | Bug | Trade Spend Sandbox ¦ Step 2 Category Issues | Brand | Trade Spend Sandbox | Unspec | High | Reopened | Md Mashiul Azam Chowdhury | Constance Wolfe | 6/21/2025 | 11/10/2025
CS-1032 | Task | [BE] Reports > Promoted Case Allowance -Please start | Reports | Reports (Unspecified) | BE | High | In Progress | Bijoy Chandra Nath | Constance Wolfe | 7/1/2025 | 9/25/2025 | Q1
CS-1037 | Bug | [BE] No error message when uploading a blank file | Admin | CRM Data Upload | BE | Low | Backlog | Bijoy Chandra Nath | Fariha Jabin | 7/1/2025 | 11/10/2025 | Q1
CS-1042 | Bug | banner edit modal  sometimes retailer name shows retailer id | Admin | CRM Data Upload | Unspec | Low | Reopened | Md Mashiul Azam Chowdhury | Fariha Jabin | 7/1/2025 | 11/17/2025
CS-1038 | Bug | [BE] Template files dont show required/mandatory fields | Admin | Admin (General) | BE | High | Backlog | Bijoy Chandra Nath | Fariha Jabin | 7/1/2025 | 11/10/2025 | Q1
CS-1039 | Bug | [BE] Field mismatch between manual form and upload template | Admin | Admin (General) | BE | Medium | Backlog | Bijoy Chandra Nath | Fariha Jabin | 7/1/2025 | 11/10/2025 | Fixed?
CS-1035 | Epic | Admin bug tickets | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/1/2025 | 7/14/2025
CS-1036 | Bug | newly created items not appearing without refresh | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Low | Ready for Production | Md Mashiul Azam Chowdhury | Fariha Jabin | 7/1/2025 | 11/18/2025 | Provide update
CS-1040 | Bug | ui issue  button corners broken | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 7/1/2025 | 11/10/2025 | Fixed?
CS-1045 | Bug | brand name should be unique | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Fixed?
CS-1046 | Bug | brand description not fully visible if too long | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Fixed?
CS-1047 | Bug | blank file upload shows unclear error | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Fixed?
CS-1048 | Bug | brand upload template includes extra column | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Q1
CS-1049 | Bug | brand owner  email search filter not working | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Q2
CS-1050 | Bug | brand  export is not working | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Q2
CS-1059 | Task | crm module  delete option missing in all modules except banner | Brand | Pipeline | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 7/7/2025 | 7/7/2025 | ??
CS-1065 | Bug | if sub brand ID is deactivated by admin, logged-in user can still access system | Broker Dashboard | Broker Dashboard (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/9/2025 | 11/10/2025 | Q3
CS-1062 | Bug | banner profile page: if name field empty, try to save, cant save, no error message shown | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/9/2025 | 11/10/2025 | Fixed?
CS-1063 | Bug | banner profile page: change password is not working | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/9/2025 | 11/10/2025 | Fixed?
CS-1064 | Bug | login: if password is less than 6 characters, sign-up fails with no error message | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/9/2025 | 11/10/2025 | Q1
CS-1072 | Task | [BE] Broker Dashboard> Update landing page to match Brand environments. Replace dashboard with Broker Logo | Broker Dashboard | Broker Dashboard (General) | BE | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 7/15/2025 | 11/6/2025 | Q2/Q3
CS-1077 | Task | Product Specs Add Product Change Order & Names of Fields | Brand | Product Specs | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 7/22/2025 | 7/22/2025 | Q2
CS-1078 | Bug | Invite User - role - brand - Select All checkbox behaves incorrectly | Admin | User Management | Unspec | Low | Backlog |  | Fariha Jabin | 7/22/2025 | 11/10/2025 | ??
CS-1090 | Task | Editing and Pushing from Trade spend sandbox will update corresponding Promo Planning | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 8/6/2025 | 8/6/2025 | Complete?
CS-1092 | Sub-task | [FE] Editing and Pushing from Trade spend sandbox will update corresponding Promo Planning | Brand | Trade Spend Sandbox | FE | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 8/6/2025 | 8/6/2025 | Fixed?
CS-1095 | Bug | [FE] Slight Glitch after editing a promo event | Brand | Trade Spend Sandbox | FE | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 8/8/2025 | 10/20/2025 | Complete?
CS-1112 | Task | product category change causes pricing to show "pricing not set" | Brand | Product Specs | Unspec | Low | Reopened | Bijoy Chandra Nath | Fariha Jabin | 8/14/2025 | 11/6/2025
CS-1118 | Bug | CRM>Pipeline>Back Button Issue | Brand | Pipeline | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 8/19/2025 | 11/10/2025 | Q2
CS-1132 | Bug | When clicking the Add New Event button, the modal shows a visual glitch. | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 8/25/2025 | 10/20/2025 | Complete?
CS-1150 | Task | CRM ¦ Pipeline - Need Undo option in task edit | Brand | Pipeline | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 8/29/2025 | 9/25/2025 | Q2
CS-1149 | Bug | Reports ¦ Category Review Uploads & Data Pushes | Reports | Category Review Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 8/29/2025 | 11/10/2025 | CR Needs Discussion
CS-1159 | Bug | Folders ¦ Download causing Errors | Broker Dashboard | Files | Unspec | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 9/8/2025 | 11/10/2025 | See Ticket 1179
CS-1162 | Task | [FE] Store Insight whole report delete by filter | Reports | Retail Reports | FE | High | Reopened | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 9/10/2025 | 11/6/2025
CS-1163 | Task | Background job for All Export | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | In Progress | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 9/10/2025 | 11/6/2025 | Provide update
CS-1164 | Task | [FE] 30 MB max size message for import | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | FE | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 9/10/2025 | 11/6/2025 | Q1
CS-1166 | Task | [BE] Check email delivery status for new Sign up | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | BE | Medium | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 9/10/2025 | 11/6/2025 | Complete?
CS-1174 | Task | Trade Spend ¦ Sandbox and Approved Have back button from results page take user to same year | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 9/20/2025 | 9/25/2025 | Complete?
CS-1177 | Bug | The "Everyday Allowance" field does not retain entered data when navigating back from later steps. | Brand | Trade Spend Sandbox | Unspec | High | Ready for Production | Md Mashiul Azam Chowdhury | Fariha Jabin | 9/22/2025 | 11/18/2025 | Provide update
CS-1178 | Task | EDLP events look the same as other events; there should be a different color, tag, or indicator to easily identify EDLP events. | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 9/22/2025 | 10/20/2025 | Q2
CS-1179 | Bug | Files ¦ Downloads still have errors see details | Broker Dashboard | Files | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 9/26/2025 | 11/10/2025 | Q1
CS-1185 | Bug | TSS ¦ Create an EDLP Promotion Only Creates Error | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/1/2025 | 11/10/2025 | Fixed?
CS-1186 | Bug | TSS ¦ Duplicating a Promotion Issue- Comments are not included in the copy | Brand | Trade Spend Sandbox | Unspec | High | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 10/2/2025 | 11/10/2025 | Provide Update
CS-1187 | Bug | Trade Spend Sandbox ¦ Ad Fees Step 4 Issue¦ If multiple events are selected the Ad Fee is split among all items in all events | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/4/2025 | 11/10/2025 | Q1
CS-1190 | Task | Trade Spend Roll Up Report ¦ Add Column for Total Trade Spend that Adds the TPR Spend w/ Ad/TPR Fees | Reports | Trade Spend Rollup | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/11/2025 | 10/11/2025 | Q2
CS-1192 | Bug | bugs relates to EDLP | Brand | Trade Spend Sandbox | Unspec | High | In Staging | Md Mashiul Azam Chowdhury | Fariha Jabin | 10/20/2025 | 11/17/2025 | Provide update
CS-1193 | Task | TSS>Step 4> Multiple Edit Divide Ad Fees by Product for Each Event Separately | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/20/2025 | 10/20/2025 | Q1
CS-1196 | Task | TSS>Add Coupon Option> | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/21/2025 | 10/21/2025 | Q2
CS-1197 | Task | TSS> Add Sku to existing event > Allow user to choose multiple events | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/22/2025 | 10/27/2025 | Q2
CS-1199 | Bug | CRM> Retailers>Promo $Rules> Upload option doesn't work> Other Notes in Description | Brand | Retailers | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/23/2025 | 11/10/2025 | Q2
CS-1201 | Bug | Fix filter so User only see the Retailers they manage, the TSS & BAP Promotions they create and the Promotions on the Calendar | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/27/2025 | 11/10/2025 | Q2
CS-1202 | Task | Promotional Calendar: If Event stretches across more than 1 month, show it on all months that are included | Brand | Promotional Calendar | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/27/2025 | 10/27/2025 | Q1 or Q2
CS-1203 | Bug | Reports>Broker Market Activity Report throws Error | Reports | Broker Market Activities | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/28/2025 | 11/10/2025 | ??
CS-1204 | Bug | Reports > Retail Report Activities Filter Doesn't Work | Reports | Retail Reports | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/28/2025 | 11/10/2025 | Q1
CS-1209 | Bug | TSS> Add A Sku to Existing Issues | Brand | Trade Spend Sandbox | Unspec | Highest | In Staging | Md Mashiul Azam Chowdhury | Constance Wolfe | 11/1/2025 | 12/22/2025 | Provide Update
CS-1211 | Task | [BE] CRM - Retailers> Newest Dates at the top of the list | Brand | Retailers | BE | Highest | In Staging | Bijoy Chandra Nath | Bijoy Chandra Nath | 11/4/2025 | 11/5/2025 | Provide Update
CS-1212 | Bug | TSS> Add EDLP to Existing Promotion > 2nd Pop Up Box only displays 1 Product | Brand | Trade Spend Sandbox | Unspec | Highest | Ready for Production | Md Mashiul Azam Chowdhury | Constance Wolfe | 11/5/2025 | 12/22/2025 | Provide Update
CS-1223 | Task | Remove legacy SPINS data  keep only filtered, relevant datasets. | Reports | SPINS | Unspec | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Q1
CS-1222 | Task | Build and validate the Single Distributor Report. | Reports | Distributor Report | Unspec | High | In Progress |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | In Progress
CS-1214 | Task | Implement and test Crisp integration Or Data Scrapping (API connection, data sync). | Admin | Data Mapping | Unspec | High | In Progress | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/24/2025 | Complete?
CS-1216 | Task | Data Mapping Expansion  Phase 2 | Admin | Data Mapping | Unspec | High | In Progress |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 12/1/2025
CS-1219 | Task | Integrate with the Data Mapping module to ensure mapped fields align during import/export. | Admin | Data Mapping | Unspec | High | In Progress |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Complete?
CS-1213 | Task | Resolve all email service reliability issues | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/24/2025 | Complete?
CS-1217 | Task | [BE] Implement the Upload/Download Wizard to handle imports/exports. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | BE | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 11/6/2025 | 1/29/2026 | Complete?
CS-1218 | Task | Remove the 30MB upload restriction (target: 200MB+). | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Complete?
CS-1220 | Task | Conduct end-to-end QA with real-world data samples. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | QA | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Q1
CS-1221 | Task | Integrate Tableau Reporting into the platform. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Not Doing
CS-1224 | Task | Conduct year-end QA, finalize documentation, and prepare release packages. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | QA | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Q1
CS-1225 | Task | CRM > Distributor > Unlink Banner > Remove restriction that it's tied up in a Promotion | Brand | Distributors | Unspec | Highest | In Progress | Bijoy Chandra Nath | Constance Wolfe | 11/8/2025 | 11/11/2025 | Provide Update
CS-1230 | Task | Reports>Trade Spend Roll Up > Updates on Headers (Net to Gross) + other Minor Changes | Reports | Trade Spend Rollup | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 11/17/2025 | 11/17/2025 | Still some items to complete
CS-1236 | Bug | TSS- New bugs | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Bijoy Chandra Nath | Fariha Jabin | 11/27/2025 | 12/9/2025 | Complete?
CS-1240 | Task | Trade Spend Calculations | Brand | Trade Spend Sandbox | Unspec | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 12/11/2025 | 12/11/2025 | Complete?
CS-1239 | Task | [BE] Forecast related endpoint implementation (Export) | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | BE | Highest | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 12/11/2025 | 12/11/2025 | Provide Update
CS-1244 | Bug | TSS Details Page: Pricing, Allowance, Total Spend, Alert UI, and TPR Fee Calculation Issues | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Bijoy Chandra Nath | Fariha Jabin | 12/24/2025 | 12/24/2025 | Q1
CS-1246 | Task | [BE] Add Gross Unit Calculation in Roll up report | Reports | Trade Spend Rollup | BE | High | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 12/24/2025 | 12/24/2025 | ??
CS-1248 | Task | TSS> Add Ad Fees/TPR Fees (Lump Sum) that's not associated with any promotion | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 12/29/2025 | 12/29/2025 | Q1
CS-1254 | Bug | [BE] Trade Spend Sandbox - New & Discontinued Items Not Calculating according to Add & Disco. Date | Brand | Trade Spend Sandbox | BE | Highest | In Staging | Bijoy Chandra Nath | Constance Wolfe | 1/9/2026 | 1/20/2026
CS-1256 | Task | New Filter For Distributor Report | Reports | Distributor Report | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 1/10/2026 | 1/10/2026 | Q1
CS-1258 | Bug | TSS  View & Edit Promo: Multiple clicks on date edit cause application error | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 1/21/2026 | 1/21/2026 | Q2
CS-1266 |  | [BE] Data Mapping > Unmapped Filter Needs Options for all Properties | Admin | Data Mapping | BE | Highest | Reopened | Bijoy Chandra Nath | Constance Wolfe | 3/24/2026 | 5/24/2026
CS-1268 |  | [BE] Data Mapping > Allow user to change status (any) in unmapped data | Admin | Data Mapping | BE | Highest | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 3/24/2026 | 5/21/2026
CS-1273 |  | TSS> View & Edit Promo Events Details > If product status changes in Retail CRM > Should the date in the Event Details Reflect the date. See decription | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/26/2026 | 4/23/2026
CS-1299 |  | Broker Dashboard Updates > APL + Add Log Market Overview | Broker Dashboard | Market Overview | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 5/4/2026
CS-1307 |  | Home Page Banner Report > Add Scroll option | Broker Dashboard | Market Overview | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1310 |  | Broker Dashboard Market Overview > Store List Not populating | Broker Dashboard | Market Overview | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/4/2026
CS-1296 |  | Broker Dashboard ¦ Category Review Calendar Rollup | Broker Dashboard | Category Review | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/28/2026
CS-1305 |  | Broker Dashboard Update UI to match the rest of the platform | Broker Dashboard | Broker Dashboard (General) | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1291 |  | Reports ¦ Category Review when Reviews are uploaded in Brand Environment It's pushing to all Brands | Reports | Category Review Report | Unspec | Medium | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/4/2026
CS-1297 |  | New Report ¦ Retail Portal Data Upload | Reports | Retail Reports | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1306 |  | Report ¦ Sales Tracking for Prospects | Reports | Sales Tracker | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 6/23/2026
CS-1283 |  | Monthly Report ¦ Importing Actuals (Manually and Automated) | Reports | Monthly Report | Unspec | High | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/21/2026
CS-1285 |  | Monthly Report ¦ Need Category in Filter w/ Dependancy for Products | Reports | Monthly Report | Unspec | High | In Progress | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/5/2026
CS-1293 |  | Reports ¦ SPINS SPINS > Prep system to accept all measures | Reports | SPINS | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1294 |  | Report SPINS Updates | Reports | SPINS | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1275 |  | Distributor Report ¦ UNFI Continue testing the crawler service to ensure it can handle website changes | Reports | Distributor Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/4/2026
CS-1278 |  | Distributor Report ¦ Should we be able to do manual uploads? | Reports | Distributor Report | Unspec | High | In Staging | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/13/2026
CS-1279 |  | Distributor Report Discussion ¦ Auto Update Retailer CRM Item Status (From NA/Pending) to Active | Reports | Distributor Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/11/2026
CS-1281 |  | Distributor Report ¦ Auto Flags for New and Disco Items/Retailers | Reports | Distributor Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/13/2026
CS-1286 |  | Distributor Report ¦ Reorganize Filter | Reports | Distributor Report | Unspec | High | In Progress | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 5/7/2026
CS-1276 |  | Current UNFI & KeHE Reports > Determine if we should use them generically | Reports | Distributor Report | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1295 |  | New Report ¦ Banner to DC Reporting | Reports | Banner-to-DC (New Report) | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 6/23/2026
CS-1308 |  | Admin >CRM Data Upload > Stores > Edit Store Name failure | Admin | CRM Data Upload | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1309 |  | Admin CRM Data Upload>Stores > Can we add Delete Button | Admin | CRM Data Upload | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1292 |  | Data Uploads ¦ Implement Dynamic Data Uploads to support formats that don't match templates (Import Wizard) | Admin | CRM Data Upload | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1290 |  | ADMIN ¦ Invite Broker > The Email Said it was inviting user as Sub Broker instead of Broker | Admin | User Management | Unspec | Medium | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/4/2026
CS-1288 |  | Ask Caboodle ¦ Coordinate with ML/AI engineer > Implement Character Requirements for Billing | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1318 |  | Broker Dashboard ¦ Market Overview Filter Needs more Field Options List Too Limited | Broker Dashboard | Market Overview | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/2/2026 | 5/4/2026
CS-1315 |  | Category Review ¦ Export All Data only Exports the current Page | Broker Dashboard | Category Review | Unspec | High | In Progress | Bijoy Chandra Nath | Constance Wolfe | 4/2/2026 | 5/5/2026
CS-1316 |  | Category Review ¦ Implement Scrolling vs pages | Broker Dashboard | Category Review | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/2/2026 | 5/4/2026
CS-1317 |  | Category Review ¦ UI/UX Consider more modern look/feel See sample | Broker Dashboard | Category Review | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/2/2026 | 5/4/2026
CS-1312 |  | Distributor Report ¦ Adjust UNFI Sales Dollars Calculations to match Distributor MOD pricing in Caboodle | Reports | Distributor Report | Unspec | High | In Progress | Bijoy Chandra Nath | Constance Wolfe | 4/2/2026 | 5/11/2026
CS-1324 |  | Broker Dashboard ¦ Promotional Management Only push Brand Approved Promotions to Promo Management | Broker Dashboard | Promotional Management | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/3/2026 | 5/4/2026
CS-1319 |  | Category Review ¦ Adding Retailers with multiple Reviews Produces Duplicates of the Retailer in the Filter (Also see CS-1320) | Broker Dashboard | Category Review | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/3/2026 | 4/3/2026
CS-1320 |  | Category Review ¦ Add Log Error Invalid Month Even though the month is Valid | Broker Dashboard | Category Review | Unspec | High | Reopened | Bijoy Chandra Nath | Constance Wolfe | 4/3/2026 | 5/18/2026
CS-1326 |  | Enhance Broker Dashboard Market Overview Functionality | Broker Dashboard | Market Overview | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1328 |  | Improve Broker Promotional Management Export and Approval Flow | Broker Dashboard | Promotional Management | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1329 |  | Fix Category Review Data Isolation and Upload Issues | Broker Dashboard | Category Review | Unspec | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1330 |  | Improve Category Review UX, Navigation and Export | Broker Dashboard | Category Review | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1327 |  | Fix Broker Dashboard Navigation and UI Issues | Broker Dashboard | Broker Dashboard (General) | Unspec | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1339 |  | Enhance Trade Spend Rollup Report with Hyperlinks and Spend Totals | Reports | Trade Spend Rollup | Unspec | Highest | Reopened | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/5/2026
CS-1335 |  | Fix Monthly Report Calculations and Data Refresh Issues | Reports | Monthly Report | Unspec | Highest | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1336 |  | Improve Monthly Report Layout, Filtering and Navigation | Reports | Monthly Report | Unspec | Highest | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/12/2026
CS-1333 |  | Fix Distributor Report Calculations and Data Consistency | Reports | Distributor Report | Unspec | Highest | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/16/2026
CS-1334 |  | Improve Distributor Report Filtering, Naming and Export | Reports | Distributor Report | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1331 |  | Enhance Data Mapping Module Usability and Filtering | Admin | Data Mapping | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1325 |  | Improve Broker Invitation and Brand Environment Setup | Admin | User Management | Unspec | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1341 |  | Margin Calculator ¦ POP Out Calculator | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/9/2026 | 5/4/2026
CS-1342 |  | Admin ¦ CRM Data Upload > Stores Upload Issue | Admin | CRM Data Upload | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/10/2026 | 5/4/2026
CS-1343 |  | [BE] Data Mapping ¦ Re-Resolve Not Working | Admin | Data Mapping | BE | High | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 4/10/2026 | 5/21/2026
CS-1348 |  | CRM ¦ Pipeline - Formatting Issue - Items cut off | Brand | Pipeline | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/21/2026 | 4/21/2026
CS-1349 |  | CRM Pipeline ¦ Enhance Editing Widget | Brand | Pipeline | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/21/2026 | 4/21/2026
CS-1347 |  | Banner List Not Sorted in Ascending Order in Retail Report > Products | Reports | Retail Reports | Unspec | Medium | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 4/21/2026 | 4/21/2026
CS-1351 |  | TSS ¦ Can Brands or Admin Adjust the Budget Threshold that turns the graph red if a Trade Spend % is Above 15% | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/22/2026 | 4/22/2026
CS-1353 |  | TSS ¦ Add 3 new Columns to Event Summary | Brand | Trade Spend Sandbox | Unspec | High | In Progress | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/24/2026 | 4/28/2026
CS-1354 |  | TSS ¦ Discussion for providing Actual Lift (Placeholder Ticket) | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/24/2026 | 4/24/2026
CS-1352 |  | Monthly Report ¦ YOY Report Needs Date Selection Option | Reports | Monthly Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/24/2026 | 5/11/2026
CS-1356 |  | [Admin] If current Session is over then User should automatically be logged out | Admin | Admin (General) | Unspec | Medium | In Progress | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/27/2026 | 5/5/2026
CS-1361 |  | Broker Dashboard ¦ New Category Review Functionality | Broker Dashboard | Category Review | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/29/2026 | 6/17/2026
CS-1363 |  | Broker Dashboard ¦ APL Add Distributor to the Filter | Broker Dashboard | Distributor APL | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/29/2026 | 4/29/2026
CS-1362 |  | Broker Dashboard ¦ Ask Caboodle | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/29/2026 | 4/29/2026
CS-1364 |  | CRM Data Upload ¦ Error Occurs When Updating Store from Stores Section | Admin | CRM Data Upload | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 4/30/2026 | 4/30/2026
CS-1365 |  | CRM Data Upload ¦ Regions List UI Not Properly Formatted in Retailers Section | Admin | CRM Data Upload | Unspec | Low | Backlog |  | Taslima Akbar Keya | 4/30/2026 | 4/30/2026
CS-1366 |  | Data Mapping ¦ Mapping Status Not Immediately Updated Across Pagination in Unmapped Records | Admin | Data Mapping | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 4/30/2026 | 4/30/2026
CS-1367 |  | Broker Dashboard Promo Management ¦ Export Data Does not Match Filter Data | Broker Dashboard | Promotional Management | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/2/2026 | 5/2/2026
CS-1369 |  | CRM Contacts ¦ Include title with the name | Brand | Contacts | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/2/2026 | 5/2/2026
CS-1368 |  | Admin ¦ Caboodle Admin needs to access all Environments w/o the need for their login credentials | Admin | Admin (General) | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/2/2026 | 5/2/2026
CS-1370 |  | User Management ¦ First Name Column Overlaps with Role Column on Window Resize (?80%) in User Management | Admin | User Management | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/3/2026 | 5/12/2026
CS-1372 |  | TSS - Everyday Allowance Field Displays 0 Despite Having Value | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Bijoy Chandra Nath | Fariha Jabin | 5/4/2026 | 5/4/2026
CS-1375 |  | [BE] Trade Spend Roll Up Report ¦ Add Column for Total Trade Spend that Adds the TPR Spend w/ Ad/TPR Fees | Reports | Trade Spend Rollup | BE | Highest | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 5/5/2026 | 5/5/2026
CS-1379 |  | User Managemnet ¦ Invitation Registration Link Redirects Logged-In Users to Login Page Instead of Signup Page | Admin | User Management | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/10/2026 | 5/12/2026
CS-1377 |  | User Managemnet ¦ Resend Invitation Button Does Not Send New Invitation Email | Admin | User Management | Unspec | Medium | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/10/2026 | 5/12/2026
CS-1378 |  | User Managemnet ¦ Prevent Multiple Pending Invitations for the Same Brand Owner Role | Admin | User Management | Unspec | Medium | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/10/2026 | 5/12/2026
CS-1376 |  | User Managemnet ¦ Show Proper Error Message for Cancelled Invitation Signup Attempt | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/10/2026 | 5/12/2026
CS-1386 |  | Product Specs ¦ Reorganize Tabs to this order: Categories > Products > Pricing | Brand | Product Specs | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/11/2026 | 5/11/2026
CS-1381 |  | TSS: Stores Field Accepts Negative Values in Add SKU Modal | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Fariha Jabin | 5/11/2026 | 5/11/2026
CS-1382 |  | TSS ? Promotion Fees ? Products from Other Banners Are Displayed in Add Promotion Fee Modal | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Fariha Jabin | 5/11/2026 | 5/11/2026
CS-1384 |  | Admin Banner Sku Upload Failed Records ¦ Please Review errors: The provided banner name doesn't match any existing Caboodle System banners | Admin | CRM Data Upload | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 5/11/2026 | 5/12/2026
CS-1388 |  | Monthly Report ¦ Add Month to Filter | Reports | Monthly Report | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/14/2026
CS-1387 |  | Admin ¦ Data Sync Not working > Not Populating Distributor Report | Reports | Distributor Report | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/12/2026
CS-1389 |  | Data Mapping ¦ Remove old Brand Data | Admin | Data Mapping | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/12/2026
CS-1390 |  | Admin ¦ Data Mapping ¦ New Bot Implementation for Broker Brands | Admin | Data Mapping | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/12/2026
CS-1391 |  | Data Mapping ¦ Banner Sku Upload | Admin | Data Mapping | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/12/2026
CS-1392 |  | User Management ¦ User Enrollment | Admin | User Management | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1393 |  | User Management ¦ Invited Users List Showing Unknown as User Type | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1394 |  | User Management ¦ Broker Invitation Email Sent as Sub-Broker Causing Invitation Acceptance Failure | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1395 |  | User Managemnet ¦ Phone Number Field Accepts Invalid Input Without Validation | Admin | User Management | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1396 |  | User Managemnet ¦ View Brand Info Label is Misleading as Users Can Also Add Brands | Admin | User Management | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1397 |  | User Managemnet ¦ Brand Assignment Modal Flow is Confusing for Reassigning Brands | Admin | User Management | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1398 |  | User Managemnet ¦ No Role Removal Option Available in Assign Role Modal for Already Assigned Users | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1399 |  | User Managemnet ¦ Incorrect Filter Columns Displayed in Invited Users Section | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1403 |  | Broker Dashboard ¦ APL Upload Adjust for UNFI UPC Codes | Broker Dashboard | Distributor APL | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/13/2026 | 5/13/2026
CS-1400 |  | Product Specs ¦ Updating Spec UPC Code causing Error | Brand | Product Specs | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/13/2026 | 5/13/2026
CS-1402 |  | [FE] Distributor Sales Report ¦ Import functionality | Reports | Distributor Report | FE | High | In Staging | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 5/13/2026 | 5/13/2026
CS-1405 |  | [BE] Monthly Report ¦ Add Month to Filter | Reports | Monthly Report | BE | Low | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 5/14/2026 | 5/14/2026
CS-1406 |  | Switching from Broker Dashboard to Brand Dashboard Sometimes Does Not Work | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Fariha Jabin | 5/18/2026 | 5/18/2026
CS-1408 |  | Broker Dashboard > APL Report > Filter showing multiple listings for same item | Broker Dashboard | Distributor APL | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/20/2026 | 5/20/2026
CS-1407 |  | Distributor Report ¦ Update DC Cases Sold Report CSV File Name | Reports | Distributor Report | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/20/2026 | 5/20/2026
CS-1409 |  | [BE] Data Mapping ¦ Allow user to cancel the exportation of Unmapped Records | Admin | Data Mapping | BE | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/21/2026 | 5/21/2026
CS-1410 |  | [FE] Data Mapping ¦ Unmapped Filter: Ordered the hierarchy of the filters based on the entity, mapping status | Admin | Data Mapping | FE | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/21/2026 | 5/21/2026
CS-1411 |  | [FE] Data Mapping ¦ Filter : Refresh page removes the filter | Admin | Data Mapping | FE | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/21/2026 | 5/21/2026
CS-1412 |  | Data Mapping ¦ Add export and filter related some new feature | Admin | Data Mapping | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/21/2026 | 5/25/2026
CS-1413 |  | TSS ¦ Promotion Fee Value Column show 0 Value if not Filtered | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/23/2026 | 5/23/2026
CS-1414 |  | TSS Promo Fee ¦ Needs a Edit Option | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/23/2026 | 5/23/2026
CS-1415 |  | Data Mapping ¦ Unmapped Store List | Admin | Data Mapping | Unspec | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 5/26/2026 | 6/1/2026
CS-1416 |  | Data Mapping Filter Issue | Admin | Data Mapping | Unspec | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 5/27/2026 | 6/1/2026
CS-1417 |  | Broker Dashboard ¦ Category Review Filter & Upload Issues | Broker Dashboard | Category Review | Unspec | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 5/30/2026 | 6/4/2026
CS-1419 |  | Admin CRM Data Upload Stores ¦ Remove Duplicates & Resolve Multi-Mapping | Admin | CRM Data Upload | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/5/2026 | 6/5/2026
CS-1418 |  | Data Mapping/CRM Data Upload ¦ Stores Add A Store Field list is missing State | Admin | Data Mapping | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/5/2026 | 6/5/2026
CS-1421 |  | Distributor Report ¦ Velocity Calculations Need Review | Reports | Distributor Report | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/17/2026 | 6/20/2026
CS-1422 |  | Product Specs & Distributor Report KEHE Master Pack Issue | Reports | Distributor Report | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/17/2026 | 6/20/2026
CS-1423 |  | Broker Dashboard ¦ Category Review Propagation | Broker Dashboard | Category Review | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 6/20/2026 | 6/21/2026
CS-1424 | Task | Data Mapping ¦ Broker Dashboard APL ¦ Need Data Sync for Broker Distributor APL | Broker Dashboard | Distributor APL | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/23/2026 | 6/23/2026
CS-1259 | Bug | TSS > Change Message for pushing a promotion to Approved > Currently says push to trade spend | Brand | Trade Spend Sandbox | Unspec | High | Backlog |  |  |  |  | Q2
CS-1429 | Sub-task | [FE] Admin Sent Emails screen with resend & bulk resend | Admin | Admin |  | High | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 2026-07-01 17:06 | 2026-07-01 17:08
CS-1428 | Sub-task | [BE] Email log API with single & bulk resend | Admin | Admin |  | High | In Progress | Kazi Towfiq Tasmin Ornov | Md Mashiul Azam Chowdhury Efti | 2026-07-01 17:04 | 2026-07-02 11:09
CS-1427 | Story | Admin - View sent email log with resend and bulk resend | Admin | Admin |  | High | In Progress | Kazi Towfiq Tasmin Ornov | Md Mashiul Azam Chowdhury Efti | 2026-07-01 17:03 | 2026-07-02 11:09
CS-1426 | Bug | Distributor Report ¦ POD Calculation is incorrect | Brand | Distributor Report |  | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 2026-06-30 20:07 | 2026-07-01 09:55
CS-1425 | Task | CRM>Pipeline > Change Plan to Project > Hide/Archive Option > See Details | Brand | CRM Pipeline |  | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 2026-06-27 02:07 | 2026-06-27 02:07
CS-1436 | Task | TSS ¦ EDLP Promotional Reporting only Populating the Month of January | Brand | TSS/Reports |  | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 2026-07-08 00:53 | 2026-07-08 00:53
CS-1435 | Task | Data Mapping ¦ Pulling in KeHE POD Current Year QTY 0 (It Should Not) | Admin | Data Mapping |  | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 2026-07-07 23:39 | 2026-07-07 23:39
CS-1433 | Bug | Distributor Report ¦ Pulling in Prior Year Sales ¦ It sould only pull in Current Year Sales | Brand | Distributor Report |  | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 2026-07-07 23:34 | 2026-07-07 23:34
CS-1432 | Task | User-Managemet: Replace Role-Specific Invite Email Templates with a Shared Template | Admin | Admin |  | Medium | In Progress | Kazi Towfiq Tasmin Ornov | Md Mashiul Azam Chowdhury Efti | 2026-07-07 12:20 | 2026-07-07 12:21
CS-1431 | Bug | Monthly Report ¦ Import Actuals > Failed Records Reason seem invalid | Brand | Monthly Report |  | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 2026-07-07 01:28 | 2026-07-07 11:03
CS-1430 | Story | Setup & Develop SNS Webhook to Receive Email Sending Events | Admin | Admin |  | High | In Progress | Kazi Towfiq Tasmin Ornov | Md Mashiul Azam Chowdhury Efti | 2026-07-05 14:44 | 2026-07-06 09:04

## Broker Dashboard
Broker Dashboard — 33 tickets
Issue Key | Type | Summary | Area | Caboodle Module | FE/BE | Priority | Status | FE | BE | QA | Assignee | Reporter | Created | Updated | Due / Note
▸ Market Overview (6)
CS-1299 |  | Broker Dashboard Updates > APL + Add Log Market Overview | Broker Dashboard | Market Overview | Unspec | High | Backlog |  |  |  | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 5/4/2026 | STORY 1326
Moved to Brand Mondule (Home Page)
CS-1310 |  | Broker Dashboard Market Overview > Store List Not populating | Broker Dashboard | Market Overview | Unspec | High | Backlog | 30m | 1h | 30m | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/4/2026 | STORY 1326
CS-1318 |  | Broker Dashboard ¦ Market Overview Filter Needs more Field Options List Too Limited | Broker Dashboard | Market Overview | Unspec | High | Backlog | 3h | 2h | 1h | Bijoy Chandra Nath | Constance Wolfe | 4/2/2026 | 5/4/2026 | STORY 1326
CS-1326 |  | Enhance Broker Dashboard Market Overview Functionality | Broker Dashboard | Market Overview | Unspec | High | Backlog |  |  |  | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026 | STORY
CS-688 | Task | [BE] Implement read tables for Market Overview | Broker Dashboard | Market Overview | BE | High | In Progress |  | 4h | 2h | Bijoy Chandra Nath | Bijoy Chandra Nath | 2/5/2025 | 9/25/2025 | Provide update
▸ Promotional Management (5)
CS-1324 |  | Broker Dashboard ¦ Promotional Management Only push Brand Approved Promotions to Promo Management | Broker Dashboard | Promotional Management | Unspec | High | Backlog |  | 2h | 1h | Bijoy Chandra Nath | Constance Wolfe | 4/3/2026 | 5/4/2026 | STORY 1328
CS-1328 |  | Improve Broker Promotional Management Export and Approval Flow | Broker Dashboard | Promotional Management | Unspec | High | Backlog |  |  |  | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026 | STORY
CS-1367 |  | Broker Dashboard Promo Management ¦ Export Data Does not Match Filter Data (Does not work at all) | Broker Dashboard | Promotional Management | Unspec | High | Backlog |  | 3h | 1h | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/2/2026 | 5/2/2026
CS-234 | Task | [BE] Promotional Management - Push date submission to brand side | Broker Dashboard | Promotional Management | BE | Medium | Backlog |  |  |  | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/21/2023 | 12/21/2023
CS-232 | Task | [BE] Promotional Management - Published distributor pricing for Promo Submissions | Broker Dashboard | Promotional Management | BE | Low | Backlog |  |  |  | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/21/2023 | 12/21/2023
▸ Category Review (11)
CS-1417 | In Staging | Broker Dashboard ¦ Category Review Filter & Upload Issues | Broker Dashboard | Category Review | Unspec | Highest | Backlog |  |  |  | Bijoy Chandra Nath | Constance Wolfe | 5/30/2026 | 6/4/2026
CS-1296 | Done | Broker Dashboard ¦ Category Review Calendar Rollup | Broker Dashboard | Category Review | Unspec | High | Backlog |  |  |  | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/28/2026 | STORY 1327
CS-1315 | Done | Category Review ¦ Export All Data only Exports the current Page | Broker Dashboard | Category Review | Unspec | High | In Progress |  |  |  | Bijoy Chandra Nath | Constance Wolfe | 4/2/2026 | 5/5/2026 | STORY 1330
CS-1316 |  | Category Review ¦ Implement Scrolling vs pages | Broker Dashboard | Category Review | Unspec | High | Backlog | 2h |  | 10m | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/2/2026 | 5/4/2026 | STORY 1330
CS-1317 | Redundend | Category Review ¦ UI/UX Consider more modern look/feel See sample | Broker Dashboard | Category Review | Unspec | High | Backlog |  |  |  | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/2/2026 | 5/4/2026 | STORY 1330 This Example is a Loveable Design for a new functionality
CS-1319 | Done | Category Review ¦ Adding Retailers with multiple Reviews Produces Duplicates of the Retailer in the Filter (Also see CS-1320) | Broker Dashboard | Category Review | Unspec | High | Backlog |  |  |  | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/3/2026 | 4/3/2026
CS-1320 | Done | Category Review ¦ Add Log Error Invalid Month Even though the month is Valid | Broker Dashboard | Category Review | Unspec | High | Reopened |  |  |  | Bijoy Chandra Nath | Constance Wolfe | 4/3/2026 | 5/18/2026
CS-1329 |  | Fix Category Review Data Isolation and Upload Issues | Broker Dashboard | Category Review | Unspec | High | Backlog |  |  |  | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1330 |  | Improve Category Review UX, Navigation and Export | Broker Dashboard | Category Review | Unspec | High | Backlog |  |  |  | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026 | STORY
CS-1361 | Redundend | Broker Dashboard ¦ New Category Review Functionality | Broker Dashboard | Category Review | Unspec | High | Backlog |  |  |  | Bijoy Chandra Nath | Constance Wolfe | 4/29/2026 | 6/17/2026 | SEE Ticket 1317
CS-1423 | Done | Broker Dashboard ¦ Category Review Propagation | Broker Dashboard | Category Review | Unspec | High | Backlog |  |  |  | Bijoy Chandra Nath | Constance Wolfe | 6/20/2026 | 6/21/2026
▸ Distributor APL (4)
CS-1424 | Task | Data Mapping ¦ Broker Dashboard APL ¦ Need Data Sync for Broker Distributor APL | Broker Dashboard | Distributor APL | Unspec | Highest | Backlog | 2h | 6d |  | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/23/2026 | 6/23/2026
CS-1363 |  | Broker Dashboard ¦ APL Add Distributor & Product (make dependent to brand) to the Filter | Broker Dashboard | Distributor APL | Unspec | High | Backlog | 2h | 4h | 1h | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/29/2026 | 4/29/2026
CS-1403 |  | Broker Dashboard ¦ APL Upload Adjust for UNFI UPC Codes | Broker Dashboard | Distributor APL | Unspec | High | Backlog |  | 4h | 1h | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/13/2026 | 5/13/2026
CS-1408 |  | Broker Dashboard > APL Report > Filter showing multiple listings for same item | Broker Dashboard | Distributor APL | Unspec | High | Backlog |  | CS-1363 |  | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/20/2026 | 5/20/2026
▸ Files (3)
CS-1159 | Bug | Folders ¦ Download causing Errors | Broker Dashboard | Files | Unspec | Highest | Backlog |  |  |  | Bijoy Chandra Nath | Constance Wolfe | 9/8/2025 | 11/10/2025 | See Ticket 1179
CS-1179 | Bug | Files ¦ Downloads still have errors see details | Broker Dashboard | Files | Unspec | Highest | Backlog |  |  |  | Md Mashiul Azam Chowdhury | Constance Wolfe | 9/26/2025 | 11/10/2025 | Q1
CS-658 | Bug | Files ¦ Files Tree Display issues See image of overlapping folders | Broker Dashboard | Files | Unspec | High | Backlog | 4h |  | 30m | Md Mashiul Azam Chowdhury | Constance Wolfe | 12/6/2024 | 4/27/2025 | ??
▸ Broker Dashboard (General) (4)
CS-1072 | Task | [BE] Broker Dashboard> Update landing page to match Brand environments. Replace dashboard with Broker Logo | Broker Dashboard | Broker Dashboard (General) | BE | High | Backlog |  |  |  | Bijoy Chandra Nath | Constance Wolfe | 7/15/2025 | 11/6/2025 | Q2/Q3
CS-1305 |  | Broker Dashboard Update UI to match the rest of the platform | Broker Dashboard | Broker Dashboard (General) | Unspec | High | Backlog |  |  |  | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1327 |  | Fix Broker Dashboard Navigation and UI Issues | Broker Dashboard | Broker Dashboard (General) | Unspec | High | Backlog |  |  |  | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1065 | Bug | if sub brand ID is deactivated by admin, logged-in user can still access system | Broker Dashboard | Broker Dashboard (General) | Unspec | Low | Backlog |  |  |  |  | Fariha Jabin | 7/9/2025 | 11/10/2025 | Q3
Need
|  | SUMMARY | Area
BROKER DASHBOARD
| 2026-07-20 | Caboodle Dashboard update for CS 1324 CW Made Edits | Broker Dashboarad | CS-1324: Broker Dashboard ¦ Promotional Management Only push Brand Approved Promotions to Promo Management
CS-1072 | 2026-07-20 | [BE] Broker Dashboard> Update landing page to match Brand environments. Replace dashboard with Broker Logo | Broker Dashboarad
|  | ASK CABOODLE | Broker Dashboarad
| BD1 | Dashboard Tasks | Broker Dashboarad
| BD2 | Assign time and person | Broker Dashboarad
| BD3 | Dashboard Filter My tasks or contact name | Broker Dashboarad
| PM7 | Broker Dashboard Button should have Broker Logo |  | CW NEEDS TO REVIEW
| BD4 | Pipeline in Broker Dashboard | NEW
CATEGORY REVIEW
| CR1 | Remove all Reviews at once rather than page by page | Category Review | Complete
|  | Category Review Email Notification See link https://lovable.dev/projects/932320d2-ce2b-4b52-ad38-ba5a2a214dc1 | Category Review
| CR3 | Allow user to increase the rows at the bottom (infinenate Scroll) | Catgegory Review | Ticket 1316
CR4 | 2026-07-20 | Calendar Sort by Banner or Category? |  | Both are typed Question (rather than User Story) since they're explicitly open questions, and both link to the relevant existing tickets (CS-1296, CS-1316, CS-1361, CR4). Not yet committed.
CR5 | 2026-07-20 | Category Review List now has Review End Date: Do we need to change the upload template?
DISTRIBUTOR APL
| DA1 | Allow infinite scrolling | Distributor APL
| DA2 | Edit requires a Wholesale Case Cost But Does not require that information during the Upload | Distributor APL
MARKET OVERVIEW
| MO1 | Edit Log needs to allow user to edit: DC | Market Overview
| MO2 | Search Option? | Market Overview
| MO3 | Check and confirm Heirarchy of Status Upldates to Brand CRM | Market Overview | CW NEEDS TO REVIEW
| MO4 | Number of Stores (Reporting Banner Door Count) This can be misleading KeHE/UNFI Independents = # Entered? | Market Overview | CW NEEDS TO REVIEW
| MO5 | Add Log Ensure user can enter multiple stores | Market Overview | CW NEEDS TO REVIEW
| MO6 | Add Log Consider Entering 1 Retailer/Multiple Brands | Market Overview
|  | Add Log Does Distribution Center need to be Required? | Market Overview
|  | Editing the Comment in the Log Can this Add new rather than override? | Market Overview
|  | Push Updates to Brands via Email (Summary click here for details) | Market Overview
PROMO MANAGEMENT
PM7 (BUG) | NEED | Submission Button Does not work | Promotional Management
| PM2 | Export Push to a Formatted Report Option (to save user from exporting then formatting) | Promotional Management | CW NEEDS TO REVIEW
| PM3 | Implement Promo Status Options currurently found in Brand Promo Calendars (Active/Cancelled/Pending/Did Not Run/Declined/Retailer Approved/Completed/Submitted)in the Submission Button. Currently this is activated in TSS) Tagged by User login | Promotional Management | CW NEEDS TO REVIEW
| PM4 | Notes Section (On top) : Allow User to Pin or Freeze Filter Options Example Useful for the year so user doesn't have to filter for the current year everytime the access the page) | Promotional Management | CW NEEDS TO REVIEW
| PM5 | Format the Grid more uniformily (each month is a difference size) | Promotional Management | CW NEEDS TO REVIEW
| PM6 | Allow the Event to move across months if the dates span multiple months | Promotional Management | CW NEEDS TO REVIEW

## Brand Modules
Brand — 56 tickets
Issue Key | Type | Summary | Area | Caboodle Module | FE/BE | Priority | Status | Assignee | Reporter | Created | Updated | Due / Note
▸ Product Specs (8)
CS-478 | Bug | Product Specs Price List ¦ Price Change is not flowing thru Trade Spend for promos after date change | Brand | Product Specs | Unspec | Highest | Reopened | Bijoy Chandra Nath | Constance Wolfe | 4/25/2024 | 7/9/2024
CS-1077 | Task | Product Specs Add Product Change Order & Names of Fields | Brand | Product Specs | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 7/22/2025 | 7/22/2025 | Q2
CS-1386 |  | Product Specs ¦ Reorganize Tabs to this order: Categories > Products > Pricing | Brand | Product Specs | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/11/2026 | 5/11/2026 | Complete
CS-1400 |  | Product Specs ¦ Updating Spec UPC Code causing Error | Brand | Product Specs | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/13/2026 | 5/13/2026
CS-617 | Sub-task | [BE] Manufacture Discontinue ¦ MFR Disco Status | Brand | Product Specs | BE | High | In Progress | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 9/26/2024 | 1/7/2025 | Provide update
CS-280 | Task | [BE] Product Specs Add a text box for Shelf Life and another for Attributes. Doesn't need to be in the file upload | Brand | Product Specs | BE | Medium | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 1/1/2024 | 1/1/2024 | Don't Do
CS-376 | Task | Product Specs - Add Chck Box for Manufacturer Discontinued | Brand | Product Specs | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 2/10/2024 | 4/27/2025 | Complete?
CS-1112 | Task | product category change causes pricing to show "pricing not set" | Brand | Product Specs | Unspec | Low | Reopened | Bijoy Chandra Nath | Fariha Jabin | 8/14/2025 | 11/6/2025
▸ Distributors (1)
CS-1225 | Task | CRM > Distributor > Unlink Banner > Remove restriction that it's tied up in a Promotion | Brand | Distributors | Unspec | Highest | In Progress | Bijoy Chandra Nath | Constance Wolfe | 11/8/2025 | 11/11/2025 | Provide Update
▸ Retailers (3)
CS-1211 | Task | [BE] CRM - Retailers> Banner Activities Newest Dates at the top of the list | Brand | Retailers | BE | Highest | In Staging | Bijoy Chandra Nath | Bijoy Chandra Nath | 11/4/2025 | 11/5/2025 | Provide Update
CS-1199 | Bug | CRM> Retailers>Promo $Rules> Upload option doesn't work> Other Notes in Description | Brand | Retailers | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/23/2025 | 11/10/2025 | Q2
CS-992 | Sub-task | [BE] Retailer details page - Category search returning irrelevant results | Brand | Retailers | BE | Low | In Progress | Bijoy Chandra Nath | Fariha Jabin | 6/4/2025 | 9/25/2025 | Provide update
▸ Contacts (1)
CS-1369 |  | CRM Contacts ¦ Include title with the name | Brand | Contacts | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/2/2026 | 5/2/2026
▸ Pipeline (5)
CS-1118 | Bug | CRM>Pipeline>Back Button Issue | Brand | Pipeline | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 8/19/2025 | 11/10/2025 | Q2
CS-1348 |  | CRM ¦ Pipeline - Formatting Issue - Items cut off | Brand | Pipeline | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/21/2026 | 4/21/2026
CS-1349 |  | CRM Pipeline ¦ Enhance Editing Widget | Brand | Pipeline | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/21/2026 | 4/21/2026
CS-1150 | Task | CRM ¦ Pipeline - Need Undo option in task edit | Brand | Pipeline | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 8/29/2025 | 9/25/2025 | Q2
CS-1425 | Task | CRM>Pipeline > Change Plan to Project > Hide/Archive Option > See Details | Brand | CRM Pipeline |  | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 2026-06-27 02:07 | 2026-06-27 02:07
CS-1059 | Task | crm module  delete option missing in all modules except banner | Brand | Pipeline | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 7/7/2025 | 7/7/2025 | ??
▸ Trade Spend Sandbox (37)
CS-1209 | Bug | TSS> Add A Sku to Existing Issues | Brand | Trade Spend Sandbox | Unspec | Highest | In Staging | Md Mashiul Azam Chowdhury | Constance Wolfe | 11/1/2025 | 12/22/2025 | Provide Update
CS-1212 | Bug | TSS> Add EDLP to Existing Promotion > 2nd Pop Up Box only displays 1 Product | Brand | Trade Spend Sandbox | Unspec | Highest | Ready for Production | Md Mashiul Azam Chowdhury | Constance Wolfe | 11/5/2025 | 12/22/2025 | Provide Update
CS-1240 | Task | Trade Spend Calculations | Brand | Trade Spend Sandbox | Unspec | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 12/11/2025 | 12/11/2025 | Complete?
CS-1254 | Bug | [BE] Trade Spend Sandbox - New & Discontinued Items Not Calculating according to Add & Disco. Date | Brand | Trade Spend Sandbox | BE | Highest | In Staging | Bijoy Chandra Nath | Constance Wolfe | 1/9/2026 | 1/20/2026
CS-725 | Story | Trade Spend Promotion Module | Brand | Trade Spend Sandbox | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Bijoy Chandra Nath | 3/12/2025 | 3/12/2025 | ??
CS-1022 | Bug | Trade Spend Sandbox ¦ Step 2 Category Issues | Brand | Trade Spend Sandbox | Unspec | High | Reopened | Md Mashiul Azam Chowdhury | Constance Wolfe | 6/21/2025 | 11/10/2025
CS-1090 | Task | Editing and Pushing from Trade spend sandbox will update corresponding Promo Planning | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 8/6/2025 | 8/6/2025 | Complete?
CS-1092 | Sub-task | [FE] Editing and Pushing from Trade spend sandbox will update corresponding Promo Planning | Brand | Trade Spend Sandbox | FE | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 8/6/2025 | 8/6/2025 | Fixed?
CS-1095 | Bug | [FE] Slight Glitch after editing a promo event | Brand | Trade Spend Sandbox | FE | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 8/8/2025 | 10/20/2025 | Complete?
CS-1174 | Task | Trade Spend ¦ Sandbox and Approved Have back button from results page take user to same year | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 9/20/2025 | 9/25/2025 | Complete?
CS-1177 | Bug | The "Everyday Allowance" field does not retain entered data when navigating back from later steps. | Brand | Trade Spend Sandbox | Unspec | High | Ready for Production | Md Mashiul Azam Chowdhury | Fariha Jabin | 9/22/2025 | 11/18/2025 | Provide update
CS-1185 | Bug | TSS ¦ Create an EDLP Promotion Only Creates Error | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/1/2025 | 11/10/2025 | Fixed?
CS-1186 | Bug | TSS ¦ Duplicating a Promotion Issue- Comments are not included in the copy | Brand | Trade Spend Sandbox | Unspec | High | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 10/2/2025 | 11/10/2025 | Provide Update
CS-1187 | Bug | Trade Spend Sandbox ¦ Ad Fees Step 4 Issue¦ If multiple events are selected the Ad Fee is split among all items in all events | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/4/2025 | 11/10/2025 | Q1
CS-1192 | Bug | bugs relates to EDLP | Brand | Trade Spend Sandbox | Unspec | High | In Staging | Md Mashiul Azam Chowdhury | Fariha Jabin | 10/20/2025 | 11/17/2025 | Provide update
CS-1193 | Task | TSS>Step 4> Multiple Edit Divide Ad Fees by Product for Each Event Separately | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/20/2025 | 10/20/2025 | Q1
CS-1236 | Bug | TSS- New bugs | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Bijoy Chandra Nath | Fariha Jabin | 11/27/2025 | 12/9/2025 | Complete?
CS-1244 | Bug | TSS Details Page: Pricing, Allowance, Total Spend, Alert UI, and TPR Fee Calculation Issues | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Bijoy Chandra Nath | Fariha Jabin | 12/24/2025 | 12/24/2025 | Q1
CS-1248 | Task | TSS> Add Ad Fees/TPR Fees (Lump Sum) that's not associated with any promotion | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 12/29/2025 | 12/29/2025 | Q1
CS-1258 | Bug | TSS  View & Edit Promo: Multiple clicks on date edit cause application error | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 1/21/2026 | 1/21/2026 | Q2
CS-1259 | Bug | TSS > Change Message for pushing a promotion to Approved > Currently says push to trade spend | Brand | Trade Spend Sandbox | Unspec | High | Backlog |  |  |  |  | Q2
CS-1273 |  | TSS> View & Edit Promo Events Details > If product status changes in Retail CRM > Should the date in the Event Details Reflect the date. See decription | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/26/2026 | 4/23/2026
CS-1353 |  | TSS ¦ Add 3 new Columns to Event Summary | Brand | Trade Spend Sandbox | Unspec | High | In Progress | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/24/2026 | 4/28/2026
CS-1413 |  | TSS ¦ Promotion Fee Value Column show 0 Value if not Filtered | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/23/2026 | 5/23/2026
CS-1414 |  | TSS Promo Fee ¦ Needs a Edit Option | Brand | Trade Spend Sandbox | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/23/2026 | 5/23/2026
CS-653 | Task | Caboodle Broker ¦ Trade Spend Sandbox should report to Promotional Management (not Promo Planning) | Brand | Trade Spend Sandbox | Unspec | High | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 11/26/2024 | 11/6/2025 | Provide update
CS-1196 | Task | TSS>Add Coupon Option> | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/21/2025 | 10/21/2025 | Q2
CS-1197 | Task | TSS> Add Sku to existing event > Allow user to choose multiple events | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/22/2025 | 10/27/2025 | Q2
CS-1201 | Task | Fix filter so User only see the Retailers they manage, the TSS & BAP Promotions they create and the Promotions on the Calendar | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/27/2025 | 11/10/2025 | Moved to Admin
CS-1351 |  | TSS ¦ Can Brands or Admin Adjust the Budget Threshold that turns the graph red if a Trade Spend % is Above 15% | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/22/2026 | 4/22/2026
CS-1354 |  | TSS ¦ Discussion for providing Actual Lift (Placeholder Ticket) | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/24/2026 | 4/24/2026
CS-1132 | Bug | When clicking the Add New Event button, the modal shows a visual glitch. | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 8/25/2025 | 10/20/2025 | Complete?
CS-1178 | Task | EDLP events look the same as other events; there should be a different color, tag, or indicator to easily identify EDLP events. | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 9/22/2025 | 10/20/2025 | Q2
CS-1372 |  | TSS - Everyday Allowance Field Displays 0 Despite Having Value | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Bijoy Chandra Nath | Fariha Jabin | 5/4/2026 | 5/4/2026
CS-1381 |  | TSS: Stores Field Accepts Negative Values in Add SKU Modal | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Fariha Jabin | 5/11/2026 | 5/11/2026
CS-1382 |  | TSS ? Promotion Fees ? Products from Other Banners Are Displayed in Add Promotion Fee Modal | Brand | Trade Spend Sandbox | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Fariha Jabin | 5/11/2026 | 5/11/2026
CS-1436 | Task | TSS ¦ EDLP Promotional Reporting only Populating the Month of January | Brand | TSS/Reports |  | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 2026-07-08 00:53 | 2026-07-08 00:53
CS-532 | Task | Trade Spend ¦ Promo Event Details ¦ Is it possible to add a sku without going thru the stepper again? | Brand | Trade Spend Sandbox | Unspec | Low | Backlog |  | Constance Wolfe | 5/28/2024 | 5/28/2024 | Complete?
▸ Promotional Calendar (1)
CS-1202 | Task | Promotional Calendar: If Event stretches across more than 1 month, show it on all months that are included | Brand | Promotional Calendar | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/27/2025 | 10/27/2025 | Q1 or Q2
HOME PAGE
CS-1307 |  | Home Page Banner Report > Add Scroll option | Broker Dashboard | Market Overview | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
Need
|  | SUMMARY | Area
| Added 7/27/26 | BRAND DASHBOARD | Brand Dashboard
|  | Update Brand Dashboard Similar to Broker Dashboard | Brand Dashboard
|  | Include Ask Caboodle | Brand Dashboard |  | Created by Efti Spring 2026
|  | See mock up from Efti from Spring 2026 (Screenshot to the right) | Brand Dashboard
Flags alerting user of upcoming Task, promotional submission, category Review Deadlines
PIPELINE
Added Ticket 1425 |  | Allow User to Hide or Archive Plans | Pipeline
|  | Label The Plans Project | Pipeline
|  | Allow User to Hide Complete Tasks (Check Box) | Pipeline
|  | Allow User to enter Due Date | Pipeline
|  | Create Calendar View for Deadlines | Pipeline
BMP1 | NEW 7/20 | Allow User to assign to Users (It adds email but not assignments) | Pipelione
BMP2 |  | Option to not send email for every update (currently everytime there is an update it sends an email to everyone, even if it's just an edit. For example if users simply corrects a spelling and hits save, it sends an email to everyone assigned to the task. When the other users get the email, it's not clear why they are getting an update, it appears nothing has changed. | Pipeline
RETAIL REPORT
|  | Display Dashboard Summary see this link https://lovable.dev/projects/8385ee0b-effd-4a8f-8cb9-27477a3fccfc | Retailers
TSS
BMTSS1 | NEW 7/20 | Remove or Modify Approved Promotions
BMTSS2 |  | Currently there is no option to remove a promotion from Approved Promotions, once it’s approved. The current work around is to delete the promotion that was Approved from the Sandbox. The SOP is to create a copy of the Approved Promotion in the Sandbox and add this to the name of the Promotion "Original Version” Date, User Initial’. Then the original version is deleted. Modifying Approved Promotions If the User wants to make any changes to the Approved Promotion, the user creates a copy of the Original Version, then edits the name to reflect “Revised, Date, Users Initials” Then modifications to the this version of the Sandbox are made, then pushed to Approved. This is to preserve all versions of the promotion if changes are made.
BMTSS3 | New 7/29 | EDLP in Stepper needs some clarification. Currently a user can enter an EDLP in the stepper. They can also add it in the Trade Spend Results page in the Edit promo details section. We need to clarify when it should be used in the stepper and when it should be used in the edit promo details. NOTE: it may depend on if the user is trying to enter both an EDLP and temporary price reductions...vs. just an EDLP | TSS
Question: Promotional Year: User Needs Clarification for if it's important to set the year in the TSS before starting a promotion. For example it's 2026 now but I want to build a promotion for 2027, Does the user need to change the year on the main page or can they start in the year of 2026 and ener 2027 dates when they build the promotion? See Screen shots to the right
BMTSS4 |  | Actualize Promotions: What is best method to actualize promotions? Currently we advise users to make a copy of the original promotion and enter the actuals from an external data sourse. However the Data source is in the system, so is there a way to automate this process? We should also have some reports aroud plan to actual | TSS
BMTSS5 | 2026-07-29 | EDIT PROMO DETAILS User needs a little more space at the bottom of Promo event details if only 1 row is showing. See Screenshot to the right | TSS
BMTSS6 |  | EDLP is showing up in the Promotional Calendar only in the month of Jan. It should be across all months. It's working correctly in Broker Promotional Management. It might be because it's still pulling from the TSS not Approved? Same is happening in the Monthly Report | TSS/Promo Calendar
| NEW 7/20 | PRODUCT SPEC
BMTPS1 |  | Add Product UPC to Pricing Module | Product Specs
RETAILER CRM
BMTRC1 |  | Add store level listing from Banner Page. It could be a link to a new page within Caboodle. See the STORE REPORT MGMT Tab | CRM
Important findings before writing — data/jira-tickets shows strong overlap:
BMTSS3 (EDLP stepper vs edit details) → directly matches CS-1302 ("determine if this should be added in the Promo Results Page … or Step 4 Metrics in the stepper").
BMTSS4 (Actualize) → there's already a working file CS-NEW-brand-tss-actualize-promotions.md in tickets/trade-spend/, plus Jira CS-1280 (Actuals Auto Updated from Distributor Reports), CS-1283, CS-1335.
BMTSS6 (EDLP only in Jan) → exact match with Jira CS-1436 ("EDLP Promotional Reporting only Populating the Month of January … works in Broker Promotional Management … same in Monthly Report").
BMTSS1/BMTSS2 (remove/modify approved) → related to CS-1122 (copy-to-approved SOP, cancelled-event indication), CS-1208 (can't rename in BAP), CS-1183 (TSS↔BAP inconsistency), CS-1160.
BMTSS5 (promo details spacing) → context cluster CS-1188/CS-1239/CS-827 (Edit Promo Event Details).

## STORE REPORT MGMT
Concept: Many Brands have a direct to store program for smaller stores. They need a way to keep track of orders and communications.
Proposed Caboodle Solution: Upload brand Store list into a separate Distributor report but very similar to the current one. Call it "House Accounts" (NOTE: I've been wanting to utilize the old UNFI & KeHE reports for agnotic reporting anyway so this may be a good solution)
See Distributor Reports> Sales Details where store names, addresses and order details are provided via uplaod
The void report could be converted to stores instead of warehouses so user can viscualize gaps in orders
Install a email automation & Trigger API that allows users to build trigger logic for emails. For example 30-day inactivity…or lifecycle automation
Need to think about email templates, I don't know that we want to get into template builders but maybe we utilize claude design? Or they could simply copy & paste a design into an editor?
These 2 charts are for inspiration > It outlines how we already ingest and report very similar data
SRM1

## Reports
Reports — 41 tickets
Issue Key | Type | Summary | Area | Caboodle Module | FE/BE | Priority | Status | Assignee | Reporter | Created | Updated | Due / Note
▸ Broker Market Activities (1)
CS-1203 | Bug | Reports>Broker Market Activity Report throws Error | Reports | Broker Market Activities | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/28/2025 | 11/10/2025 | ??
▸ Category Review Report (2)
CS-1149 | Bug | Reports ¦ Category Review Uploads & Data Pushes | Reports | Category Review Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 8/29/2025 | 11/10/2025 | STORY 1329
CS-1291 |  | Reports ¦ Category Review when Reviews are uploaded in Brand Environment It's pushing to all Brands | Reports | Category Review Report | Unspec | Medium | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/4/2026 | STORY 1329
▸ Retail Reports (4)
CS-1204 | Bug | Reports > Retail Report Activities Filter Doesn't Work | Reports | Retail Reports | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/28/2025 | 11/10/2025 | Q1
CS-1162 | Task | [FE] Store Insight whole report delete by filter | Reports | Retail Reports | FE | High | Reopened | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 9/10/2025 | 11/6/2025
CS-1297 |  | New Report ¦ Retail Portal Data Upload | Reports | Retail Reports | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1347 |  | Banner List Not Sorted in Ascending Order in Retail Report > Products | Reports | Retail Reports | Unspec | Medium | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 4/21/2026 | 4/21/2026
▸ Sales Tracker (1)
CS-1306 |  | Report ¦ Sales Tracking for Prospects | Reports | Sales Tracker | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 6/23/2026
▸ Trade Spend Rollup (5)
CS-1190 | Task | Trade Spend Roll Up Report ¦ Add Column for Total Trade Spend that Adds the TPR Spend w/ Ad/TPR Fees | Reports | Trade Spend Rollup | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/11/2025 | 10/11/2025 | Q2
CS-1339 |  | Enhance Trade Spend Rollup Report with Hyperlinks and Spend Totals | Reports | Trade Spend Rollup | Unspec | Highest | Reopened | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/5/2026
CS-1375 |  | [BE] Trade Spend Roll Up Report ¦ Add Column for Total Trade Spend that Adds the TPR Spend w/ Ad/TPR Fees | Reports | Trade Spend Rollup | BE | Highest | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 5/5/2026 | 5/5/2026
CS-1230 | Task | Reports>Trade Spend Roll Up > Updates on Headers (Net to Gross) + other Minor Changes | Reports | Trade Spend Rollup | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 11/17/2025 | 11/17/2025 | Still some items to complete
CS-1246 | Task | [BE] Add Gross Unit Calculation in Roll up report | Reports | Trade Spend Rollup | BE | High | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 12/24/2025 | 12/24/2025 | ??
▸ Monthly Report (7)
CS-1335 |  | Fix Monthly Report Calculations and Data Refresh Issues | Reports | Monthly Report | Unspec | Highest | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1336 |  | Improve Monthly Report Layout, Filtering and Navigation | Reports | Monthly Report | Unspec | Highest | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/12/2026
CS-1283 |  | Monthly Report ¦ Importing Actuals (Manually and Automated) | Reports | Monthly Report | Unspec | High | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/21/2026
CS-1285 |  | Monthly Report ¦ Need Category in Filter w/ Dependancy for Products | Reports | Monthly Report | Unspec | High | In Progress | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/5/2026
CS-1352 |  | Monthly Report ¦ YOY Report Needs Date Selection Option | Reports | Monthly Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/24/2026 | 5/11/2026
CS-1388 |  | Monthly Report ¦ Add Month to Filter | Reports | Monthly Report | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/14/2026
CS-1431 | Bug | Monthly Report ¦ Import Actuals > Failed Records Reason seem invalid | Brand | Monthly Report |  | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 2026-07-07 01:28 | 2026-07-07 11:03
CS-1405 |  | [BE] Monthly Report ¦ Add Month to Filter | Reports | Monthly Report | BE | Low | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 5/14/2026 | 5/14/2026
▸ SPINS (3)
CS-1223 | Task | Remove legacy SPINS data  keep only filtered, relevant datasets. | Reports | SPINS | Unspec | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Q1
CS-1293 |  | Reports ¦ SPINS SPINS > Prep system to accept all measures | Reports | SPINS | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1294 |  | Report SPINS Updates | Reports | SPINS | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
▸ Distributor Report (16)
CS-1333 |  | Fix Distributor Report Calculations and Data Consistency | Reports | Distributor Report | Unspec | Highest | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/16/2026
CS-1421 |  | Distributor Report ¦ Velocity Calculations Need Review | Reports | Distributor Report | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/17/2026 | 6/20/2026
CS-1422 |  | Product Specs & Distributor Report KEHE Master Pack Issue | Reports | Distributor Report | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/17/2026 | 6/20/2026
CS-1222 | Task | Build and validate the Single Distributor Report. | Reports | Distributor Report | Unspec | High | In Progress |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | In Progress
CS-1256 | Task | New Filter For Distributor Report | Reports | Distributor Report | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 1/10/2026 | 1/10/2026 | Q1
CS-1275 |  | Distributor Report ¦ UNFI Continue testing the crawler service to ensure it can handle website changes | Reports | Distributor Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/4/2026
CS-1278 |  | Distributor Report ¦ Should we be able to do manual uploads? | Reports | Distributor Report | Unspec | High | In Staging | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/13/2026
CS-1279 |  | Distributor Report Discussion ¦ Auto Update Retailer CRM Item Status (From NA/Pending) to Active | Reports | Distributor Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/11/2026
CS-1281 |  | Distributor Report ¦ Auto Flags for New and Disco Items/Retailers (Summary of update x new x disco) | Reports | Distributor Report | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/13/2026
CS-1286 |  | Distributor Report ¦ Reorganize Filter | Reports | Distributor Report | Unspec | High | In Progress | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 5/7/2026
CS-1312 |  | Distributor Report ¦ Adjust UNFI Sales Dollars Calculations to match Distributor MOD pricing in Caboodle | Reports | Distributor Report | Unspec | High | In Progress | Bijoy Chandra Nath | Constance Wolfe | 4/2/2026 | 5/11/2026 | Add Message to User about Sale Dollar from UNFI VS KeHE
CS-1334 |  | Improve Distributor Report Filtering, Naming and Export | Reports | Distributor Report | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026 | STORY
CS-1387 |  | Admin ¦ Data Sync Not working > Not Populating Distributor Report | Reports | Distributor Report | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/12/2026
CS-1402 |  | [FE] Distributor Sales Report ¦ Import functionality | Reports | Distributor Report | FE | High | In Staging | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 5/13/2026 | 5/13/2026
CS-1276 |  | Current UNFI & KeHE Reports > Determine if we should use them generically | Reports | Distributor Report | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1426 | Bug | Distributor Report ¦ POD Calculation is incorrect | Brand | Distributor Report |  | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 2026-06-30 20:07 | 2026-07-01 09:55
CS-1433 | Bug | Distributor Report ¦ Pulling in Prior Year Sales ¦ It sould only pull in Current Year Sales | Brand | Distributor Report |  | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 2026-07-07 23:34 | 2026-07-07 23:34
CS-1407 |  | Distributor Report ¦ Update DC Cases Sold Report CSV File Name | Reports | Distributor Report | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/20/2026 | 5/20/2026
▸ Banner-to-DC (New Report) (1)
CS-1295 |  | New Report ¦ Banner to DC Reporting | Reports | Banner-to-DC (New Report) | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 6/23/2026
▸ Reports (Unspecified) (1)
CS-1032 | Task | [BE] Reports > Promoted Case Allowance -Please start | Reports | Reports (Unspecified) | BE | High | In Progress | Bijoy Chandra Nath | Constance Wolfe | 7/1/2025 | 9/25/2025 | Q1
Need
|  | SUMMARY | Area
|  | DISTRIBUTOR REPORT |  | Date Added
| RDR1 | Should user be able to Export the Data? | Brand Distributor Report
| RDR2 | Only report a rolling latest 12 months unless filtered differently | Brand Distributor Report | 2026-07-07
BROKER MARKET OVERVIEW
| RBMO1 | Sort Function: There is a Date Time but it does't work. There should be a date on this list | Brand Broker Market Overiew
| RBMO2 | Needs Summary Report See Prototype | https://lovable.dev/projects/8385ee0b-effd-4a8f-8cb9-27477a3fccfc
SPINS
| RBS1 | Hide Market Insights | SPINS
|  | SALES TRACKER | Sales Tracker
| RBST1 | After clicking a retailer in a region to view the product details, there is a back button. When the user clicks the back button, it takes them to the international region no matter what region they started in. | Sales Tracker
| New 7/20 | Sales Tracker Needs a new look: See loveable link for inspiration | Sales Tracker | https://lovable.dev/projects/8385ee0b-effd-4a8f-8cb9-27477a3fccfc

## Admin
Admin — 67 tickets
Issue Key | Type | Summary | Area | Caboodle Module | FE/BE | Priority | Status | Assignee | Reporter | Created | Updated | Due / Note
▸ CRM Data Upload (11)
CS-1308 |  | Admin >CRM Data Upload > Stores > Edit Store Name failure | Admin | CRM Data Upload | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1309 |  | Admin CRM Data Upload>Stores > Can we add Delete Button | Admin | CRM Data Upload | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1342 |  | Admin ¦ CRM Data Upload > Stores Upload Issue | Admin | CRM Data Upload | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/10/2026 | 5/4/2026
CS-1384 |  | Admin Banner Sku Upload Failed Records ¦ Please Review errors: The provided banner name doesn't match any existing Caboodle System banners | Admin | CRM Data Upload | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 5/11/2026 | 5/12/2026
CS-1419 |  | Admin CRM Data Upload Stores ¦ Remove Duplicates & Resolve Multi-Mapping | Admin | CRM Data Upload | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/5/2026 | 6/5/2026
CS-496 | Bug | Banner Upload Error Messaging | Admin | CRM Data Upload | Unspec | High | Backlog |  | Constance Wolfe | 5/2/2024 | 11/10/2025 | ??
CS-1364 |  | CRM Data Upload ¦ Error Occurs When Updating Store from Stores Section | Admin | CRM Data Upload | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 4/30/2026 | 4/30/2026
CS-1037 | Bug | [BE] No error message when uploading a blank file | Admin | CRM Data Upload | BE | Low | Backlog | Bijoy Chandra Nath | Fariha Jabin | 7/1/2025 | 11/10/2025 | Q1
CS-1042 | Bug | banner edit modal  sometimes retailer name shows retailer id | Admin | CRM Data Upload | Unspec | Low | Reopened | Md Mashiul Azam Chowdhury | Fariha Jabin | 7/1/2025 | 11/17/2025
CS-1292 |  | Data Uploads ¦ Implement Dynamic Data Uploads to support formats that don't match templates (Import Wizard) | Admin | CRM Data Upload | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1365 |  | CRM Data Upload ¦ Regions List UI Not Properly Formatted in Retailers Section | Admin | CRM Data Upload | Unspec | Low | Backlog |  | Taslima Akbar Keya | 4/30/2026 | 4/30/2026
▸ Data Mapping (19)
CS-1266 |  | [BE] Data Mapping > Unmapped Filter Needs Options for all Properties | Admin | Data Mapping | BE | Highest | Reopened | Bijoy Chandra Nath | Constance Wolfe | 3/24/2026 | 5/24/2026
CS-1268 |  | [BE] Data Mapping > Allow user to change status (any) in unmapped data | Admin | Data Mapping | BE | Highest | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 3/24/2026 | 5/21/2026
CS-1331 |  | Enhance Data Mapping Module Usability and Filtering | Admin | Data Mapping | Unspec | Highest | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1415 |  | Data Mapping ¦ Unmapped Store List | Admin | Data Mapping | Unspec | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 5/26/2026 | 6/1/2026
CS-1416 |  | Data Mapping Filter Issue | Admin | Data Mapping | Unspec | Highest | Backlog | Bijoy Chandra Nath | Constance Wolfe | 5/27/2026 | 6/1/2026
CS-1214 | Task | Implement and test Crisp integration Or Data Scrapping (API connection, data sync). | Admin | Data Mapping | Unspec | High | In Progress | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/24/2025
CS-1216 | Task | Data Mapping Expansion  Phase 2 | Admin | Data Mapping | Unspec | High | In Progress |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 12/1/2025
CS-1219 | Task | Integrate with the Data Mapping module to ensure mapped fields align during import/export. | Admin | Data Mapping | Unspec | High | In Progress |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Complete?
CS-1343 |  | [BE] Data Mapping ¦ Re-Resolve Not Working | Admin | Data Mapping | BE | High | Ready for Production | Bijoy Chandra Nath | Constance Wolfe | 4/10/2026 | 5/21/2026
CS-1389 |  | Data Mapping ¦ Remove old Brand Data | Admin | Data Mapping | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/12/2026
CS-1390 |  | Admin ¦ Data Mapping ¦ New Bot Implementation for Broker Brands | Admin | Data Mapping | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/12/2026
CS-1391 |  | Data Mapping ¦ Banner Sku Upload | Admin | Data Mapping | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/12/2026 | 5/12/2026
CS-1418 |  | Data Mapping/CRM Data Upload ¦ Stores Add A Store Field list is missing State | Admin | Data Mapping | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 6/5/2026 | 6/5/2026
CS-487 | Task | [BE] Saving Banner SKU Failed Records and automatically adding them back into the system once we've matched up the unrecognized banners from the Data Mapping section | Admin | Data Mapping | BE | Medium | Backlog | Bijoy Chandra Nath | Bijoy Chandra Nath | 4/29/2024 | 9/25/2025 | ??
CS-1366 |  | Data Mapping ¦ Mapping Status Not Immediately Updated Across Pagination in Unmapped Records | Admin | Data Mapping | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 4/30/2026 | 4/30/2026
CS-1409 |  | [BE] Data Mapping ¦ Allow user to cancel the exportation of Unmapped Records | Admin | Data Mapping | BE | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/21/2026 | 5/21/2026
CS-1410 |  | [FE] Data Mapping ¦ Unmapped Filter: Ordered the hierarchy of the filters based on the entity, mapping status | Admin | Data Mapping | FE | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/21/2026 | 5/21/2026
CS-1411 |  | [FE] Data Mapping ¦ Filter : Refresh page removes the filter | Admin | Data Mapping | FE | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/21/2026 | 5/21/2026
CS-1435 | Task | Data Mapping ¦ Pulling in KeHE POD Current Year QTY 0 (It Should Not) | Admin | Data Mapping |  | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 2026-07-07 23:39 | 2026-07-07 23:39
CS-1412 |  | Data Mapping ¦ Add export and filter related some new feature | Admin | Data Mapping | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/21/2026 | 5/25/2026
▸ User Management (17)
CS-1325 |  | Improve Broker Invitation and Brand Environment Setup | Admin | User Management | Unspec | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury Efti | 4/7/2026 | 5/4/2026
CS-1379 |  | User Managemnet ¦ Invitation Registration Link Redirects Logged-In Users to Login Page Instead of Signup Page | Admin | User Management | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/10/2026 | 5/12/2026
CS-1290 |  | ADMIN ¦ Invite Broker > The Email Said it was inviting user as Sub Broker instead of Broker | Admin | User Management | Unspec | Medium | Backlog | Bijoy Chandra Nath | Constance Wolfe | 3/31/2026 | 5/4/2026
CS-1370 |  | User Management ¦ First Name Column Overlaps with Role Column on Window Resize (?80%) in User Management | Admin | User Management | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/3/2026 | 5/12/2026
CS-1377 |  | User Managemnet ¦ Resend Invitation Button Does Not Send New Invitation Email | Admin | User Management | Unspec | Medium | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/10/2026 | 5/12/2026
CS-1378 |  | User Managemnet ¦ Prevent Multiple Pending Invitations for the Same Brand Owner Role | Admin | User Management | Unspec | Medium | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/10/2026 | 5/12/2026
CS-1392 |  | User Management ¦ User Enrollment | Admin | User Management | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-562 | Task | [BE] Implement User-Based Permission Control Module | Admin | User Management | BE | Medium | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 6/24/2024 | 9/25/2025 | Provide update
CS-1078 | Bug | Invite User - role - brand - Select All checkbox behaves incorrectly | Admin | User Management | Unspec | Low | Backlog |  | Fariha Jabin | 7/22/2025 | 11/10/2025 | ??
CS-1376 |  | User Managemnet ¦ Show Proper Error Message for Cancelled Invitation Signup Attempt | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/10/2026 | 5/12/2026
CS-1393 |  | User Management ¦ Invited Users List Showing Unknown as User Type | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1394 |  | User Management ¦ Broker Invitation Email Sent as Sub-Broker Causing Invitation Acceptance Failure | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1395 |  | User Managemnet ¦ Phone Number Field Accepts Invalid Input Without Validation | Admin | User Management | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1396 |  | User Managemnet ¦ View Brand Info Label is Misleading as Users Can Also Add Brands | Admin | User Management | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1397 |  | User Managemnet ¦ Brand Assignment Modal Flow is Confusing for Reassigning Brands | Admin | User Management | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1398 |  | User Managemnet ¦ No Role Removal Option Available in Assign Role Modal for Already Assigned Users | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
CS-1399 |  | User Managemnet ¦ Incorrect Filter Columns Displayed in Invited Users Section | Admin | User Management | Unspec | Low | Backlog | Bijoy Chandra Nath | Taslima Akbar Keya | 5/12/2026 | 5/12/2026
▸ Admin (General) (20)
CS-1038 | Bug | [BE] Template files dont show required/mandatory fields | Admin | Admin (General) | BE | High | Backlog | Bijoy Chandra Nath | Fariha Jabin | 7/1/2025 | 11/10/2025 | Q1
CS-1368 |  | Admin ¦ Caboodle Admin needs to access all Environments w/o the need for their login credentials | Admin | Admin (General) | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 5/2/2026 | 5/2/2026
CS-675 | Sub-task | Empowering Brand owner's edit in Banner SKU section | Admin | Admin (General) | Unspec | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/26/2024 | 9/25/2025 | ??
CS-1039 | Bug | [BE] Field mismatch between manual form and upload template | Admin | Admin (General) | BE | Medium | Backlog | Bijoy Chandra Nath | Fariha Jabin | 7/1/2025 | 11/10/2025 | Fixed?
CS-1356 |  | [Admin] If current Session is over then User should automatically be logged out | Admin | Admin (General) | Unspec | Medium | In Progress | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 4/27/2026 | 5/5/2026
CS-146 | Task | [BE] Module on off | Admin | Admin (General) | BE | Medium | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/3/2023 | 12/3/2023 | Discuss
CS-147 | Task | [FE] Module on off | Admin | Admin (General) | FE | Medium | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 12/3/2023 | 4/27/2025 | Discuss
CS-1035 | Epic | Admin bug tickets | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/1/2025 | 7/14/2025
CS-1045 | Bug | brand name should be unique | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Fixed?
CS-1046 | Bug | brand description not fully visible if too long | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Fixed?
CS-1047 | Bug | blank file upload shows unclear error | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Fixed?
CS-1048 | Bug | brand upload template includes extra column | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Q1
CS-1049 | Bug | brand owner  email search filter not working | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Q2
CS-1050 | Bug | brand  export is not working | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/2/2025 | 11/10/2025 | Q2
CS-1062 | Bug | banner profile page: if name field empty, try to save, cant save, no error message shown | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/9/2025 | 11/10/2025 | Fixed?
CS-1063 | Bug | banner profile page: change password is not working | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/9/2025 | 11/10/2025 | Fixed?
CS-1064 | Bug | login: if password is less than 6 characters, sign-up fails with no error message | Admin | Admin (General) | Unspec | Low | Backlog |  | Fariha Jabin | 7/9/2025 | 11/10/2025 | Q1
CS-245 | Task | [BE] Admin - Activity Log | Admin | Admin (General) | BE | Low | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/21/2023 | 12/21/2023 | Discuss
CS-246 | Task | [FE] Admin - Activity Log | Admin | Admin (General) | FE | Low | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 12/21/2023 | 4/27/2025 | Discuss
CS-247 | Task | [BE] Admin - Upload Effeciency | Admin | Admin (General) | BE | Low | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 12/21/2023 | 12/21/2023 | Discuss
CS-1201 | Task | Fix filter so User only see the Retailers they manage, the TSS & BAP Promotions they create and the Promotions on the Calendar | Brand | Trade Spend Sandbox | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Constance Wolfe | 10/27/2025 | 11/10/2025 | Moved from Brand
CS-1429 | Sub-task | [FE] Admin Sent Emails screen with resend & bulk resend | Admin | Admin |  | High | Backlog | Md Mashiul Azam Chowdhury Efti | Md Mashiul Azam Chowdhury Efti | 2026-07-01 17:06 | 2026-07-01 17:08
CS-1427 | Story | Admin - View sent email log with resend and bulk resend | Admin | Admin |  | High | In Progress | Kazi Towfiq Tasmin Ornov | Md Mashiul Azam Chowdhury Efti | 2026-07-01 17:03 | 2026-07-02 11:09
CS-1432 | Task | User-Managemet: Replace Role-Specific Invite Email Templates with a Shared Template | Admin | Admin |  | Medium | In Progress | Kazi Towfiq Tasmin Ornov | Md Mashiul Azam Chowdhury Efti | 2026-07-07 12:20 | 2026-07-07 12:21
CS-1430 | Story | Setup & Develop SNS Webhook to Receive Email Sending Events | Admin | Admin |  | High | In Progress | Kazi Towfiq Tasmin Ornov | Md Mashiul Azam Chowdhury Efti | 2026-07-05 14:44 | 2026-07-06 09:04
CS-1428 | Sub-task | [BE] Email log API with single & bulk resend | Admin | Admin |  | High | In Progress | Kazi Towfiq Tasmin Ornov | Md Mashiul Azam Chowdhury Efti | 2026-07-01 17:04 | 2026-07-02 11:09
Need
CRM DATA UPLOAD
| ACDU1 | Perform Filter Audit in all CRM Data Upload > User should be able to filter by any column
DASHBOARD
| AD1 | Prototype with Flags alerting user of upcoming Task, promotional submission, category Review Deadlines
ADMIN CONTROLS
| AAC1 | Admin should be able to control the Icons on the buttons 0n the Reports Page (Example Monthly Report)
| AAC2 | Control Dropdown options for Broker Category Review Brand Report
NEED A WAY TO:
| ANAWT1 | Single Trade Spend for Basic Subscription
STORE REPORT
| ASR1 | Need to eliminate/merge store duplicates

## Platform & Cross-Cutting
Platform & Cross-Cutting — 28 tickets
Issue Key | Type | Summary | Area | Caboodle Module | FE/BE | Priority | Status | Assignee | Reporter | Created | Updated | Due / Note
▸ Infrastructure / Cross-Cutting (28)
CS-1239 | Task | [BE] Forecast related endpoint implementation (Export) | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | BE | Highest | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 12/11/2025 | 12/11/2025 | Provide Update
CS-570 | Task | Filters Updates | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Highest | Reopened | Md Mashiul Azam Chowdhury | Heather Whittier | 7/9/2024 | 4/27/2025
CS-1163 | Task | Background job for All Export | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | In Progress | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 9/10/2025 | 11/6/2025 | Provide update
CS-1164 | Task | [FE] 30 MB max size message for import | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | FE | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 9/10/2025 | 11/6/2025 | Q1
CS-1213 | Task | Resolve all email service reliability issues | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/24/2025 | Complete?
CS-1217 | Task | [BE] Implement the Upload/Download Wizard to handle imports/exports. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | BE | High | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 11/6/2025 | 1/29/2026 | Complete?
CS-1218 | Task | Remove the 30MB upload restriction (target: 200MB+). | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Complete?
CS-1220 | Task | Conduct end-to-end QA with real-world data samples. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | QA | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Q1
CS-1221 | Task | Integrate Tableau Reporting into the platform. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Not Doing
CS-1224 | Task | Conduct year-end QA, finalize documentation, and prepare release packages. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | QA | High | Backlog |  | Md Mashiul Azam Chowdhury | 11/6/2025 | 11/6/2025 | Q1
CS-1288 |  | Ask Caboodle ¦ Coordinate with ML/AI engineer > Implement Character Requirements for Billing | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 3/31/2026 | 3/31/2026
CS-1341 |  | Margin Calculator ¦ POP Out Calculator | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Bijoy Chandra Nath | Constance Wolfe | 4/9/2026 | 5/4/2026
CS-1362 |  | Broker Dashboard ¦ Ask Caboodle | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Md Mashiul Azam Chowdhury Efti | Constance Wolfe | 4/29/2026 | 4/29/2026
CS-514 | Task | Optimize the tables to ensure that the site remains unaffected even with a large amount of data. | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 5/7/2024 | 5/7/2024 | Complete?
CS-517 | Task | Apply Indexing Mechanism in Database | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 5/7/2024 | 9/25/2025 | Provide update
CS-955 | Epic | UX Audit | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | High | Backlog | Abdullah Al Mahmud | Md Mashiul Azam Chowdhury | 5/15/2025 | 11/6/2025 | ??
CS-1166 | Task | [BE] Check email delivery status for new Sign up | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | BE | Medium | Backlog | Bijoy Chandra Nath | Md Mashiul Azam Chowdhury | 9/10/2025 | 11/6/2025 | Complete?
CS-190 | Task | Caboodle Phase 2 Requirements | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Medium | Backlog |  | Md Mashiul Azam Chowdhury | 12/9/2023 | 2/5/2024
CS-405 | Task | Monitoring Service | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Medium | Backlog | Bijoy Chandra Nath | Bijoy Chandra Nath | 2/29/2024 | 9/25/2025 | ??
CS-512 | Task | Check if we can further utilize caching from any other areas | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Medium | Backlog | Md Mashiul Azam Chowdhury | Md Mashiul Azam Chowdhury | 5/7/2024 | 5/7/2024 | ??
CS-518 | Task | Automatically Remove Deleted Records After Certain Period Of Time | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Medium | Backlog | Bijoy Chandra Nath | Bijoy Chandra Nath | 5/7/2024 | 9/25/2025 | ??
CS-519 | Task | [BE] Re-Structuring The Code Base | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | BE | Medium | In Progress | Bijoy Chandra Nath | Bijoy Chandra Nath | 5/7/2024 | 9/25/2025 | Provide update
CS-1036 | Bug | newly created items not appearing without refresh | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Low | Ready for Production | Md Mashiul Azam Chowdhury | Fariha Jabin | 7/1/2025 | 11/18/2025 | Provide update
CS-1040 | Bug | ui issue  button corners broken | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury | Fariha Jabin | 7/1/2025 | 11/10/2025 | Fixed?
CS-1406 |  | Switching from Broker Dashboard to Brand Dashboard Sometimes Does Not Work | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Low | Backlog | Md Mashiul Azam Chowdhury Efti | Fariha Jabin | 5/18/2026 | 5/18/2026
CS-701 | Story | Share link of pages like in google and restrict it to view only | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | Unspec | Low | Backlog | Constance Wolfe | Md Mashiul Azam Chowdhury | 2/17/2025 | 11/6/2025 | ??
CS-894 | Epic | Issues from QA audit | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | QA | Low | Backlog |  | Fariha Jabin | 5/5/2025 | 11/6/2025 | ??
CS-973 | Story | Regression Test | Platform & Cross-Cutting | Infrastructure / Cross-Cutting | QA | Low | Backlog |  | Fariha Jabin | 5/26/2025 | 5/29/2025 | ??
Need
ENHANCEMENTS NEEDED TO SCALE TO THOUSANDS OF USERS
Caching
Big Data Management
New Brand Onbording Process Effencencies